## Note
A note about Bloom's Taxonomy
While some Learning Objectives appear to tell a trainer or coach how to teach, that is not the intent. Bloom's-style Learning Objectives describe what the learner can do upon completion of the class.
This Bloom’s style of Learning Objectives consists of six levels of learning: Knowledge, Comprehension, Application, Analysis, Synthesis, and Evaluation. The levels progress from lower order to higher order thinking skills, Knowledge through Evaluation. The level of each learning objective can be identified using the color designations above.
In the mapping document, you will notice that each action word has been color coded in order to help you align your learners measurability.

## Bloom's Staircase
case studies
|  |  |  | projects | projects
|  |  |  | problems | exercises
|  |  | problems | case studies | critiques
|  | exercises | exercises | creative exercises | simulations
| questions | practice | case studies | develop plans | appraisals
| discussion | demonstrations | critical incidents | constructs | EVALUATION
| review | projects | discussion | simulations
| test | sketches | questions | SYNTHESIS | judge
lecture | assessment | simulations | test |  | appraise
visuals | reports | role play | ANALYSIS | compose | evaluate
video | learner | microteach |  | plan | rate
audio | presentations | APPLICATION | distinguish | propose | compare
examples | writing |  | analyze | design | value
illustrations | COMPREHENSION | interpret | differentiate | formulate | revise
analogies |  | apply | appraise | arrange | score
KNOWLEDGE | translate | employ | calculate | collect | select
| restate | use | experiment | construct | choose
define | discuss | demonstrate | test | create | assess
repeat | describe | dramatize | compare | set up | estimate
record | recognize | practice | contrast | organize | measure
list | explain | illustrate | criticize | manage
| express | operate | diagram | prepare
| identify | schedule | inventory
|  | shop | questions
|  | sketch | relate

## Scrum Foundations Mapping Doc
2020 Scrum Foundations Learning Objectives
Section | Topic | Subtopic | LO# | Learning Objective | How will this Learning Objective be measured? | Reference(s) | Allotted Time | Notes
1 | Scrum Theory |  | Example | … explain, using examples, at least three unit testing principles and practices | Participants will create an advertisement/flyer for each unit testing practice/principle. (Example of writing activity from the Bloom's Staircase) | Page 34 of Student Workbook | 15 minutes
|  |  | 1.1 | … describe how Scrum is aligned with the values and principles of the Manifesto for Agile Software Development.
|  |  | 1.2 | … define Scrum and describe its purpose.
|  |  | 1.3 | … list the five core Scrum values.
|  |  | 1.4 | … define empirical process control and list the three pillars.
|  |  | 1.5 | … explain how product planning in an empirical environment differs from traditional fixed planning.
|  |  | 1.6 | … describe at least two benefits that could be lost if Scrum is only paritally implemented.
|  |  | 1.7 | … describe the benefits of an iterative and incremental approach.
2 | The Scrum Roles |  | 2.1 | … illustrate how the Scrum Roles interact with each other to deliver the Increment within a Sprint.
|  |  | 2.2 | … define a cross-functional team and identify at least three benefits of a cross-functional, self-organizing team.
3 | Scrum Events |  | 3.1 | … explain at least three benefits of timeboxing.
|  |  | 3.2 | … list the five events within Scrum, define the purpose of each event, and identify the participants, timing, and maximum recommended timebox.
4 | Scrum Artifacts |  | 4.1 | … list the three artifacts within Scrum and define the purpose of each.
|  |  | 4.2 | … explain the definition of 'Done,' its purpose, and how it evolves over time.
|  |  | 4.3 | … identify at least two reasons why the Scrum Team dedicates time for Product Backlog Refinement.
|  |  | 4.4 | … list at least three activities that may occur as part of Product Backlog Refinement.

## CSM Mapping Doc
CST Applicants: Please map the learning objectives for BOTH CSM and Scrum Foundations.
If you are applying after March 31st, 2020, you are expected to use this mapping document, NOT any prior versions.
2020 CSM Learning Objectives
Section | Topic | Subtopic | LO# | Learning Objective | How will this Learning Objective be measured? | Reference(s) | Allotted Time | Notes
1 | Lean, Agile, & Scrum |  | Example | … explain, using examples, at least three unit testing principles and practices | Participants will create an advertisement/flyer for each unit testing practice/principle. (Example of writing activity from the Bloom's Staircase) | Page 34 of Student Workbook | 15 minutes
|  |  | 1.1 | … list at least three rights and five responsibilities of the Product Owner, Development Team and Scrum Master.
|  | Scrum Roles | 1.2 | … discuss at least two reasons why the Product Owner is a single person and not a group or a committee.
|  |  | 1.3 | … discuss how and why the Product Owner maintains authority over the product while working collaboratively with the Development Team and stakeholders.
|  |  | 1.4 | … list at least five characteristics of the Development Team.
|  | Scrum Events and Artifact Transparency | 1.5 | … give one example of how a Scrum Team will inspect and adapt and increase transparency at each of the Scrum events.
|  |  | 1.6 | … describe at least three responsibilities for the Development Team, Product Owner, and Scrum Master during Sprint Planning, Daily Scrum, Sprint Review, and Retrospective.
|  | Sprint and Increment | 1.7 | … describe why the Sprint Goal does not change during a Sprint.
|  |  | 1.8 | … define the outcome of every Sprint.
|  |  | 1.9 | … discuss at least three reasons why the Increment must be brought to the current definition of 'Done' regardless of whether the Product Owner chooses to release the Increment.
|  | Sprint Planning | 1.1 | … discuss the focus of the activities of the Product Owner and Development Team during the two topics of Sprint Planning: the "What" and the "How."
|  |  | 1.11 | … practice writing a Sprint Goal.
|  | Daily Scrum | 1.12 | … discuss at least three ways the Daily Scrum differs from a status meeting; and why the various constraints exist to support the Development Team.
|  | Sprint Review | 1.13 | … describe at least three activities that occur during the Sprint Review other than a demonstration of the increment.
|  |  | 1.14 | … identify at least three potential outcomes for a Sprint Review.
|  | Sprint Retrospective | 1.15 | …describe at least two approaches to conduct a Sprint Retrospective.
|  | Product Backlog | 1.16 | … identify at least three essential characteristics of the Product Backlog.
|  |  | 1.17 | … list at least four attributes of a Product Backlog item.
|  | Sprint Backlog | 1.18 | … identify at least three essential characteristics of the Sprint Backlog.
|  |  | 1.19 | … demonstrate how the Sprint Backlog can be changed without endangering the Sprint Goal.
|  | Definition of "Done" | 1.2 | … explain the importance of a strong definition of “Done” and describe at least two risks associated with a weaker definition of “Done.”
|  |  | 1.21 | … outline at least one way to create a definition of “Done.”
|  |  | 1.22 | … identify at least two reasons why multiple teams working on the same Product Backlog have a shared and consistent definition of “Done.”
2 | Scrum Master Core Competencies | Facilitation | 2.1 | … describe at least three situations in which the Scrum Master could serve the needs of the Scrum Team or organization through facilitation.
|  |  | 2.2 | … demonstrate at least three techniques for facilitating group decision making.
|  | Coaching | 2.3 | … restate how facilitating, teaching, mentoring, and coaching are different.
|  |  | 2.4 | … apply at least one technique that could help to resolve a challenge faced by a Scrum Team.
3 | Service to the Development Team | Scrum Master as Servant-Leader | 3.1 | … define servant-leadership.
|  |  | 3.2 | … describe three scenarios where the Scrum Master acts as the servant-leader for the Development Team.
|  |  | 3.3 | … identify possible violations of Scrum by a Product Owner or stakeholder who is applying excessive time pressure and illustrate how to address them.
|  |  | 3.4 | … define technical debt and explain the impact of accumulating technical debt.
|  |  | 3.5 | … list at least three development practices that will help Scrum Teams deliver a high-quality Product Increment and reduce technical debt each Sprint.
4 | Service to the Product Owner |  | 4.1 | … explain at least three ways the Scrum Master could support the Product Owner.
|  |  | 4.2 | … list at least two benefits that arise if a Product Owner participates in the Sprint retrospective.
5 | Service to the Organization | Impediment Removal | 5.1 | … discuss at least two ways that the Scrum Master assists the Scrum Team with impediments.
|  |  | 5.2 | …describe at least three organizational impediments that can affect Scrum Teams.
|  | Coaching to the Organization | 5.3 | … describe at least one example of an organizational design change caused by adopting Scrum.
|  |  | 5.4 | … discuss why Scrum does not have a project manager and what happens to traditional project management activities.